## Sheet1
Big Mart Sales Prediction
ID |  | Title | Epic | User Story | Priority (MoSCoW) | Status | Acceptance Criteria | Functional Requirements | Non-Functional Requirements | Original Estimate | Actual Effort (In days)
1 | Sprint 1 | Data Preprocessing and Feature Engineering | Accurate Prediction of Big Mart Sales | I want to clean and preprocess the Big Mart dataset, so that I can ensure the data is ready for model training | Must | READY | Data is cleaned, missing values handled, new features created, and data normalized/scaled | Implement data cleaning, handle missing values, outlier detection, and feature engineering. | Data processing should be efficient and scalable. | 3 days | 3 days
2 |  | Baseline Model Development | Accurate Prediction of Big Mart Sales | I want to implement and test baseline models ( Linear Regression, Ridge Regression), so that I have a performance benchmark to compare against. | Must | process | Baseline models (Linear Regression, Ridge Regression) implemented with performance metrics recorded.. | Code for Linear Regression and Ridge Regression models. | Baseline models should be simple and easily interpretable. | 7 days
3 |  | XGBRF Model Development | Accurate Prediction of Big Mart Sales | I want to develop the XGBRF model, so that I can leverage the strengths of XGBoost and Random Forest for better prediction accuracy. | Must | Process | XGBRF model is implemented and hyperparameters are tuned. | Implement XGBRF model and perform hyperparameter tuning. | Model should handle large datasets efficiently. | 7 days
4 |  | Model Evaluation | Accurate Prediction of Big Mart Sales | I want to evaluate the model's performance using cross-validation and metrics like R-squared and RMSE, so that I can ensure the model is reliable. I want to compare the performance of the XGBRF model with traditional models, so that I can justify the use of advanced techniques. | Must | To Do | Model evaluated using cross-validation and metrics like R-squared, RMSE. | Code for model evaluation and comparison. | Evaluation process should be accurate and comprehensive. | 7 days
5 |  | Sales Prediction and Validation | Accurate Prediction of Big Mart Sales Using XGBRF Regressor | As a Retail Manager, I want to use the sales predictions to optimize inventory management and reduce wastage, so that I can improve the store's profitability. | Must | To Do | Predictions are made and validated against actual sales data.. | Final model prediction and validation code. | Predictions should be accurate and reliable. | 8 days